## TaskList
Project Name | Task | Assigned To | Start Date | ETA (Days) | Expected Closure Date | Days compledted Reported | Progress | Allocated Budget | Actual Till Date | % Budget Consumed | Task Status
Project-1 | Task Type 1 | Tom | 2021-02-17 | 4 | 2021-02-23 | 3 | 75% | 30 | 21 | 70% | In Progress
Project-1 | Task Type 2 | Ben | 2021-02-17 | 6 | 2021-02-25 | 4 | 66.67% | 52 | 33 | 63.46% | In Progress
Project-1 | Task Type 3 | Ginger | 2021-02-18 | 7 | 2021-03-01 | 2 | 28.57% | 64 | 46 | 71.88% | In Progress
Project-1 | Task Type 4 | Angela | 2021-02-21 | 6 | 2021-03-01 | 4 | 66.67% | 80 | 72 | 90% | In Progress
Project-1 | Task Type 5 | Hank | 2021-02-17 | 8 | 2021-03-01 | 2 | 25% | 72 | 14 | 19.44% | In Progress
Project-1 | Task Type 6 | Tom | 2021-02-20 | 2 | 2021-02-23 | 0 | 0% | 49 | 44 | 89.8% | Not Started
Project-1 | Task Type 7 | Ben | 2021-02-20 | 7 | 2021-03-02 | 2 | 28.57% | 68 | 45 | 66.18% | In Progress
Project-1 | Task Type 8 | Ginger | 2021-02-24 | 6 | 2021-03-04 | 3 | 50% | 67 | 13 | 19.4% | In Progress
Project-1 | Task Type 9 | Angela | 2021-02-24 | 5 | 2021-03-03 | 2 | 40% | 69 | 30 | 43.48% | In Progress
Project-1 | Task Type 10 | Hank | 2021-02-24 | 6 | 2021-03-04 | 1 | 16.67% | 50 | 48 | 96% | In Progress
Project-2 | Task Type 1 | Tom | 2021-02-18 | 4 | 2021-02-24 | 3 | 75% | 37 | 25 | 67.57% | In Progress
Project-2 | Task Type 2 | Ben | 2021-02-17 | 6 | 2021-02-25 | 3 | 50% | 46 | 45 | 97.83% | In Progress
Project-2 | Task Type 3 | Ginger | 2021-02-18 | 2 | 2021-02-22 | 1 | 50% | 79 | 51 | 64.56% | In Progress
Project-2 | Task Type 4 | Angela | 2021-02-20 | 2 | 2021-02-23 | 1 | 50% | 20 | 5 | 25% | In Progress
Project-2 | Task Type 5 | Hank | 2021-02-21 | 5 | 2021-02-26 | 4 | 80% | 68 | 51 | 75% | In Progress
Project-2 | Task Type 6 | Tom | 2021-02-21 | 4 | 2021-02-25 | 2 | 50% | 14 | 6 | 42.86% | In Progress
Project-2 | Task Type 7 | Ben | 2021-02-24 | 4 | 2021-03-02 | 1 | 25% | 19 | 11 | 57.89% | In Progress
Project-2 | Task Type 8 | Ginger | 2021-02-25 | 4 | 2021-03-03 | 3 | 75% | 14 | 12 | 85.71% | In Progress
Project-2 | Task Type 9 | Angela | 2021-02-27 | 5 | 2021-03-05 | 4 | 80% | 58 | 28 | 48.28% | In Progress
Project-2 | Task Type 10 | Hank | 2021-02-17 | 5 | 2021-02-24 | 0 | 0% | 26 | 5 | 19.23% | Not Started
Project-3 | Task Type 1 | Tom | 2021-02-17 | 7 | 2021-02-26 | 1 | 14.29% | 59 | 31 | 52.54% | In Progress
Project-3 | Task Type 2 | Ben | 2021-02-21 | 6 | 2021-03-01 | 3 | 50% | 60 | 27 | 45% | In Progress
Project-3 | Task Type 3 | Ginger | 2021-02-24 | 8 | 2021-03-08 | 6 | 75% | 73 | 32 | 43.84% | In Progress
Project-3 | Task Type 4 | Angela | 2021-02-26 | 3 | 2021-03-03 | 3 | 100% | 52 | 28 | 53.85% | Completed
Project-3 | Task Type 5 | Hank | 2021-02-28 | 5 | 2021-03-05 | 0 | 0% | 77 | 61 | 79.22% | Not Started
Project-4 | Task Type 1 | Tom | 2021-03-02 | 6 | 2021-03-10 | 2 | 33.33% | 47 | 36 | 76.6% | In Progress
Project-4 | Task Type 2 | Ben | 2021-03-02 | 4 | 2021-03-08 | 2 | 50% | 30 | 14 | 46.67% | In Progress
Project-4 | Task Type 3 | Ginger | 2021-02-17 | 4 | 2021-02-23 | 1 | 25% | 24 | 13 | 54.17% | In Progress
Project-4 | Task Type 4 | Angela | 2021-02-19 | 8 | 2021-03-03 | 5 | 62.5% | 67 | 49 | 73.13% | In Progress
Project-4 | Task Type 5 | Hank | 2021-02-24 | 4 | 2021-03-02 | 4 | 100% | 50 | 13 | 26% | Completed
Project-4 | Task Type 6 | Tom | 2021-02-25 | 5 | 2021-03-04 | 3 | 60% | 51 | 45 | 88.24% | In Progress
Project-4 | Task Type 7 | Ben | 2021-02-25 | 7 | 2021-03-08 | 6 | 85.71% | 38 | 13 | 34.21% | In Progress
Project-5 | Task Type 1 | Ginger | 2021-02-28 | 8 | 2021-03-10 | 7 | 87.5% | 59 | 45 | 76.27% | In Progress
Project-5 | Task Type 2 | Angela | 2021-03-02 | 4 | 2021-03-08 | 3 | 75% | 70 | 16 | 22.86% | In Progress
Project-5 | Task Type 3 | Hank | 2021-02-20 | 7 | 2021-03-02 | 4 | 57.14% | 61 | 44 | 72.13% | In Progress
Project-5 | Task Type 4 | Tom | 2021-02-19 | 5 | 2021-02-26 | 3 | 60% | 47 | 37 | 78.72% | In Progress
Project-5 | Task Type 5 | Ben | 2021-02-21 | 4 | 2021-02-25 | 3 | 75% | 56 | 16 | 28.57% | In Progress
Project-5 | Task Type 6 | Ginger | 2021-02-24 | 3 | 2021-03-01 | 2 | 66.67% | 60 | 15 | 25% | In Progress
Project-5 | Task Type 7 | Angela | 2021-02-24 | 6 | 2021-03-04 | 0 | 0% | 48 | 30 | 62.5% | Not Started
Project-5 | Task Type 8 | Hank | 2021-02-24 | 4 | 2021-03-02 | 2 | 50% | 36 | 31 | 86.11% | In Progress
Formulas:
Expected Closure Date = WORKDAY(TaskList[[#This Row],[Start Date]],TaskList[[#This Row],[ETA (Days)]])

## Dropdowns Lists
Project Name | Task Type | Assignee | Task Status
Project-1 | Task Type 1 | Tom | Not Started
Project-2 | Task Type 2 | Ben | In Progress
Project-3 | Task Type 3 | Ginger | Completed
Project-4 | Task Type 4 | Angela
Project-5 | Task Type 5 | Hank
Task Type 6
Task Type 7
Task Type 8
Task Type 9
Task Type 10

## Overall Dashboard
Overall Dashboard
Client | Task | Assigned To | Start Date | Expected Closure Date | ETA (Days) | Days compledted Reported | Progress | Allocated Budget | Actual Till Date | % Budget Consumed
Project-1 | Task Type 1 | Tom | 2021-02-17 | 2021-02-23 | 4 | 3 | 75% | 30 | 21 | 70%
Project-1 | Task Type 10 | Hank | 2021-02-24 | 2021-03-04 | 6 | 1 | 16.67% | 50 | 48 | 96%
Project-1 | Task Type 2 | Ben | 2021-02-17 | 2021-02-25 | 6 | 4 | 66.67% | 52 | 33 | 63.46%
Project-1 | Task Type 3 | Ginger | 2021-02-18 | 2021-03-01 | 7 | 2 | 28.57% | 64 | 46 | 71.88%
Project-1 | Task Type 4 | Angela | 2021-02-21 | 2021-03-01 | 6 | 4 | 66.67% | 80 | 72 | 90%
Project-1 | Task Type 5 | Hank | 2021-02-17 | 2021-03-01 | 8 | 2 | 25% | 72 | 14 | 19.44%
Project-1 | Task Type 6 | Tom | 2021-02-20 | 2021-02-23 | 2 | 0 | 0% | 49 | 44 | 89.8%
Project-1 | Task Type 7 | Ben | 2021-02-20 | 2021-03-02 | 7 | 2 | 28.57% | 68 | 45 | 66.18%
Project-1 | Task Type 8 | Ginger | 2021-02-24 | 2021-03-04 | 6 | 3 | 50% | 67 | 13 | 19.4%
Project-1 | Task Type 9 | Angela | 2021-02-24 | 2021-03-03 | 5 | 2 | 40% | 69 | 30 | 43.48%
Project-2 | Task Type 1 | Tom | 2021-02-18 | 2021-02-24 | 4 | 3 | 75% | 37 | 25 | 67.57%
Project-2 | Task Type 10 | Hank | 2021-02-17 | 2021-02-24 | 5 | 0 | 0% | 26 | 5 | 19.23%
Project-2 | Task Type 2 | Ben | 2021-02-17 | 2021-02-25 | 6 | 3 | 50% | 46 | 45 | 97.83%
Project-2 | Task Type 3 | Ginger | 2021-02-18 | 2021-02-22 | 2 | 1 | 50% | 79 | 51 | 64.56%
Project-2 | Task Type 4 | Angela | 2021-02-20 | 2021-02-23 | 2 | 1 | 50% | 20 | 5 | 25%
Project-2 | Task Type 5 | Hank | 2021-02-21 | 2021-02-26 | 5 | 4 | 80% | 68 | 51 | 75%
Project-2 | Task Type 6 | Tom | 2021-02-21 | 2021-02-25 | 4 | 2 | 50% | 14 | 6 | 42.86%
Project-2 | Task Type 7 | Ben | 2021-02-24 | 2021-03-02 | 4 | 1 | 25% | 19 | 11 | 57.89%
Project-2 | Task Type 8 | Ginger | 2021-02-25 | 2021-03-03 | 4 | 3 | 75% | 14 | 12 | 85.71%
Project-2 | Task Type 9 | Angela | 2021-02-27 | 2021-03-05 | 5 | 4 | 80% | 58 | 28 | 48.28%
Project-3 | Task Type 1 | Tom | 2021-02-17 | 2021-02-26 | 7 | 1 | 14.29% | 59 | 31 | 52.54%
Project-3 | Task Type 2 | Ben | 2021-02-21 | 2021-03-01 | 6 | 3 | 50% | 60 | 27 | 45%
Project-3 | Task Type 3 | Ginger | 2021-02-24 | 2021-03-08 | 8 | 6 | 75% | 73 | 32 | 43.84%
Project-3 | Task Type 4 | Angela | 2021-02-26 | 2021-03-03 | 3 | 3 | 100% | 52 | 28 | 53.85%
Project-3 | Task Type 5 | Hank | 2021-02-28 | 2021-03-05 | 5 | 0 | 0% | 77 | 61 | 79.22%
Project-4 | Task Type 1 | Tom | 2021-03-02 | 2021-03-10 | 6 | 2 | 33.33% | 47 | 36 | 76.6%
Project-4 | Task Type 2 | Ben | 2021-03-02 | 2021-03-08 | 4 | 2 | 50% | 30 | 14 | 46.67%
Project-4 | Task Type 3 | Ginger | 2021-02-17 | 2021-02-23 | 4 | 1 | 25% | 24 | 13 | 54.17%
Project-4 | Task Type 4 | Angela | 2021-02-19 | 2021-03-03 | 8 | 5 | 62.5% | 67 | 49 | 73.13%
Project-4 | Task Type 5 | Hank | 2021-02-24 | 2021-03-02 | 4 | 4 | 100% | 50 | 13 | 26%
Project-4 | Task Type 6 | Tom | 2021-02-25 | 2021-03-04 | 5 | 3 | 60% | 51 | 45 | 88.24%
Project-4 | Task Type 7 | Ben | 2021-02-25 | 2021-03-08 | 7 | 6 | 85.71% | 38 | 13 | 34.21%
Project-5 | Task Type 1 | Ginger | 2021-02-28 | 2021-03-10 | 8 | 7 | 87.5% | 59 | 45 | 76.27%
Project-5 | Task Type 2 | Angela | 2021-03-02 | 2021-03-08 | 4 | 3 | 75% | 70 | 16 | 22.86%
Project-5 | Task Type 3 | Hank | 2021-02-20 | 2021-03-02 | 7 | 4 | 57.14% | 61 | 44 | 72.13%
Project-5 | Task Type 4 | Tom | 2021-02-19 | 2021-02-26 | 5 | 3 | 60% | 47 | 37 | 78.72%
Project-5 | Task Type 5 | Ben | 2021-02-21 | 2021-02-25 | 4 | 3 | 75% | 56 | 16 | 28.57%
Project-5 | Task Type 6 | Ginger | 2021-02-24 | 2021-03-01 | 3 | 2 | 66.67% | 60 | 15 | 25%
Project-5 | Task Type 7 | Angela | 2021-02-24 | 2021-03-04 | 6 | 0 | 0% | 48 | 30 | 62.5%
Project-5 | Task Type 8 | Hank | 2021-02-24 | 2021-03-02 | 4 | 2 | 50% | 36 | 31 | 86.11%
Grand Total
This shape represents a slicer. Slicers are supported in Excel 2010 or later. If the shape was modified in an earlier version of Excel, or if the workbook was saved in Excel 2003 or earlier, the slicer cannot be used.
This shape represents a slicer. Slicers are supported in Excel 2010 or later. If the shape was modified in an earlier version of Excel, or if the workbook was saved in Excel 2003 or earlier, the slicer cannot be used.
This shape represents a slicer. Slicers are supported in Excel 2010 or later. If the shape was modified in an earlier version of Excel, or if the workbook was saved in Excel 2003 or earlier, the slicer cannot be used.

## Agents
Agent Name | Angela
Task Status |  | Days Status |  | Budget Status
Not Started | 1 | Allocated | 39 | Allocated | 464
In Progress | 6 | Completed | 22 | Spent | 258
Completed | 1

## Projects
PROJECTS DASHBOARD
Task Status |  |  |  |  | Days Status |  |  | Budget Status
Project Name | Not Started | In Progress | Completed |  | Project Name | ETA (Days) | Days Completed | Project Name | Allocated Budget | Actual Budget
Project-1 | 1 | 9 | 0 |  | Project-1 | 57 | 23 | Project-1 | 601 | 366
Project-2 | 1 | 9 | 0 |  | Project-2 | 41 | 22 | Project-2 | 381 | 239
Project-3 | 1 | 3 | 1 |  | Project-3 | 29 | 13 | Project-3 | 321 | 179
Project-4 | 0 | 6 | 1 |  | Project-4 | 38 | 23 | Project-4 | 307 | 183
Project-5 | 1 | 7 | 0 |  | Project-5 | 41 | 24 | Project-5 | 437 | 234
Grand Total | 4 | 34 | 2 |  | Grand Total | 206 | 105 | Grand Total | 2047 | 1201
Project 1
| Tasks Report |  |  |  | Days Report |  |  | Budget Report
Project 2
| Tasks Report |  |  |  | Days Report |  |  | Budget Report
Project 3
| Tasks Report |  |  |  | Days Report |  |  | Budget Report
Project 4
| Tasks Report |  |  |  | Days Report |  |  | Budget Report
Project 5
| Tasks Report |  |  |  | Days Report |  |  | Budget Report